## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Finishing Database | 2h |  | 2h | - | Strutzenberger, Trinkl
Starting with CS | 3h | 4h | 3h | 1h | Tischler, Punz
Fixing Music Queue | 1h |  | 1h | - | Punz