## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Socket Connect/Token | 3h |  | 3h | - | Punz
Exception Handler | 1h |  | 1h | - | Punz
First Commands/Design | 4h | 2h | 3h | 3h | Strutzenberger, Trinkl, Tischler
Discord Library learning | 2h |  | 2h | - | Strutzenberger, Punz, Trinkl, Tischler