## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
White/Blacklist Implementation | 3h |  | 3h | - | Trinkl, Punz
Coin Flip against Bot | 3h |  | 2h | - | Tischler, Trinkl
Rock Paper Scissor against Bot | 3h |  | 2h | - | Strutzenberger, Punz
Coin Flip against User | 2h |  | 1h |  | Tischler, Trinkl