## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
implementing Screenshare | 1 | 1 | 0 | 1 | Tischler
testing Pet and fixing Pet bugs | 2 | 2 | 0 | 2 | Tischler, Strutzenberger
finishing Memes | 2 | 2 | 0 | 2 | Punz
final Testing | 3 | 3 | 0 | 3 | Trinkl
merging | 2 | 2 | 0 | 2 | Punz, Strutzenberger