## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Fixing existing Errors | 5 | 5 | 5 | 0 | Tischler, Strutzenberger, Trinkl
updated help again | 1 | 1 | 1 | 0 | Strutzenberger
trying to send Videos via Screenshare | 3 | 4 | 4 | 0 | Punz | Dropped