## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Coin Flip against User | 1h |  | 1h | - | Tischler, Trinkl
Emote Handling for CT | 3h |  | 3h | - | Trinkl, Punz
Emote Handling for RPS | 3h |  | 3h | - | Strutzenberger, Punz
Adapting Shop Prices | 30min |  | 30min | - | Strutzenberger
begin implementing TicTacToe | 3h |  | 1h |  | Tischler, Strutzenberger