## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Continuing TicTacToe Implementation | 2 |  |  | 0 | Tischler, Strutzenberger | Dropped
extending Database with Pet Table | 1 | 1 | 1 | 0 | Punz
Pet buy, Pet Profile | 3 | 2 | 2 | 0 | Trinkl, Punz
Implementing Hangman | 2 | 4 | 2 | 2 | Tischler, Strutzenberger