## Tabelle1
Task | Orig. Est. | Curr. Est. | Effort | Remain | Responsible
Starting with Coin System/Remove Coin Function | 3h | 6h | 6h | - | Tischler, Punz
daily login and shop view | 3h | 4h | 4h | - | Tischler, Trinkl
music streams | 2h |  |  | 2h | Punz, Strutzenberger
!profile function | 2h |  |  | 2h | Strutzenberger
Item Storage | 2h | 4h | 3h | - | Trinkl, Punz, Strutzenberger